## Slide 1: Assessment of Water Resource Sustainability in Otter Point, Shirley And Jordan River
Pacific Priority Solutions
(RRU Bsc. Major Project Students: Kodi Bowman, Gayle Hatchard, Vickie Ntomola And Emily Rudderham)
Working With
OPSRRA Board Subcommittee: Brenda Mark, Sandy Barta And Bill Dushenko

## Slide 2: Objectives
Create a GIS map and central database of wells, water licenses, watersheds, groundwater and aquifers that is compatible with the existing databases of the CRD and provincial government, which can be archived and is easily accessible to the community
Identify information gaps in existing water source data, and potential barriers to water sustainability, as well as aquifer studies and areas for further research needed in addressing these information gaps
Summarize and critically analyze the new Water Sustainability Act in terms of its ability to ensure the sustainability of current and future water resources in the Shirley, Otter Point, and Jordan River communities.

## Slide 3: Progress to Date
Sign off of project proposal (including methodology and direction) and budget on
OPSRRA submitted a grant-in-aid proposal to CRD to fund the majority of this project, with a small contribution of funds from the OPSRRA account, as well as many in-kind hours.
OPSRRA attendance at Major Project Proposal presentations at RRU on March 18 (Brenda Mark and Sandy Barta)
Team field reconnaissance tour of communities (including CRD) with Brenda on March 29th
Team Data Gathering Continues… ArcGIS map and database, identification of information gaps, reviewing past and current Water Sustainability Acts

## Slide 4: Future Milestones
May 31st - Interim Report, including progress and financial report
June 10th – Interim Major Project Presentation
August 19th – Final Report
August 26th - Major Project Presentation and Project Financial Report